## Worksheet
Monthly Report
Start Date :2024-09-11 00:00:00
End Date : 2024-10-11 06:38:02
Incident id | Issue Type | Department | Unit No | Location | Reported BY | Issue Description | Serverity Level | Action Details | Target Date | Issue Status | Issue Created | Issue last Updated
57 | Unsafe Condition (PIO – UC) | Mechanical | 1 | Collection Pit | Samir C Patel | Suction Line Support Corroded. | Low |  | 2024-10-02 | Open | 2024-09-11 13:01:41 | 2024-09-11 13:21:51
58 | Unsafe Condition (PIO – UC) | Mechanical | 1 | Collection Pit | Samir C Patel | Circulation Line Tied With Rope. | Low |  | 2024-10-02 | Open | 2024-09-11 13:03:41 | 2024-09-11 13:21:32
59 | Unsafe Condition (PIO – UC) | Mechanical | 1 | Collection Pit | Samir C Patel | Unwanted Pipe Protuding Tripping Hazard. | Low |  | 2024-10-02 | Open | 2024-09-11 13:07:03 | 2024-09-11 13:21:14
60 | Unsafe Condition (PIO – UC) | Mechanical | 1 | Pipe rack (west side of Process building) | Samir C Patel | E.T.P. Transfer Line Shoe Support Not Fixed Up. | Low |  | 2024-10-02 | Open | 2024-09-11 13:10:39 | 2024-09-11 13:20:58
61 | Unsafe Condition (PIO – UC) | Electrical | 1 | Pipe rack | Samir C Patel | Light Fixture Hanging Condition. | Low |  | 2024-10-02 | Open | 2024-09-11 13:12:43 | 2024-09-11 13:20:37
62 | Unsafe Condition (PIO – UC) | Safety & Environment | 1 | Out side process Building | Samir C Patel | Safety Shower Sign Board Is Corroded | Low |  | 2024-10-02 | Open | 2024-09-11 13:15:21 | 2024-09-11 13:20:09
63 | Unsafe Condition (PIO – UC) | Mechanical | 1 | Near Collection Pit | Samir C Patel | Pipe Support Without '' U'clamp.' | Low |  | 2024-10-02 | Open | 2024-09-11 13:17:43 | 2024-09-11 13:19:41
64 | Near Miss | Mechanical | 3 | C1 TANKER LOADING POINT | Jayesh Desai | C1 GAS RELEASED AFTER C1 TANKER LOADING OPERATION DURING HOSE DISMENTALING. DE-PRESSURIES FACILITY NOT AVAILABLE | Moderate | Depressurisation Facilities Provided | 2024-09-27 | Closed | 2024-09-12 09:32:14 | 2024-10-11 06:35:38
65 | Unsafe Condition (PIO – UC) | Civil | 1 | Near Reactor-G | Kamlesh Patel | 02 Nos. Of Step Of Staircase Observed Detached. | Low |  | 2024-10-03 | Open | 2024-09-12 09:42:18 | 2024-09-12 09:45:38
66 | Near Miss | Mechanical | 3 | TRAIN: A DISTILLATION 1800- SECTION | Jayesh Desai | AS WE USED TEMPORARY HOSE CONNECTION FOR PURGING CRUDE LIQUIED AS PER PLANT REQUIRED WHICH RISK OF CHEMICAL SPLASHING DURING HANDLE THIS ACTIVITY | Low | Valve Closed | 2024-10-03 | Closed | 2024-09-12 10:24:48 | 2024-10-11 06:34:23
67 | Near Miss | Other | 1 | Near ETP Cabin | Darhit Shah | During Walking Near ETP Cabin Mr. M H Valand Of PAP Mechanical Department Fall Down In Civil Trench Sue To Water Logging. |  | Repeated | 2024-09-19 | Closed Request | 2024-09-12 10:25:31 | 2024-09-12 10:26:55
68 | Near Miss | Other | 1 | Near ETP Cabin | Darhit Shah | During Walking Near ETP Cabin Mr. M H Valand Of PAP Mechanical Department Fall Down In Civil Trench Sue To Water Logging. |  |  | 2024-09-19 | Open | 2024-09-12 10:25:33 | 2024-09-12 10:25:33
69 | Unsafe Condition (PIO – UC) | Civil | 1 | At 6-Meter Area near H5-312 Evaporator | Darhit Shah | Floor Opening Should Be Properly Covered To Avoid Any Unsafe Incident |  |  | 2024-09-28 | Open | 2024-09-21 06:37:46 | 2024-09-21 06:37:46
70 | Unsafe Condition (PIO – UC) | Civil | 1 | Behind Fire Water Pump House | Darhit Shah | TMT Bar Lying On Walkway. May Cause Injury To Leg By Entrapping Leg In Bar. |  |  | 2024-10-03 | Open | 2024-09-26 06:31:09 | 2024-09-26 06:31:09
71 | Unsafe Condition (PIO – UC) | Other | 1 | New Alcohol Ware House | Darhit Shah | Unwanted Pipe Piece Observed. May Cause Leg Injury In Night |  |  | 2024-10-03 | Open | 2024-09-26 06:34:03 | 2024-09-26 06:34:03
72 | Unsafe Condition (PIO – UC) | Fire | 1 | Near Warehouse - 2 | Darhit Shah | Unwanted Pipe Piece Near Ware House-2. May Cause Leg Injury |  |  | 2024-10-03 | Open | 2024-09-26 06:38:08 | 2024-09-26 06:38:08
73 | Unsafe Condition (PIO – UC) | Civil | 1 | On Raw Water Pump House | Darhit Shah | Platform Found Corroded And Damaged On Raw Water Pump House. May Cause Fall Injury. |  |  | 2024-10-03 | Open | 2024-09-26 06:40:56 | 2024-09-26 06:40:56
74 | Unsafe Condition (PIO – UC) | Electrical | 1 | 13 & 17 mtr, evaporation area | Kamlesh Patel | Poor Illimitation At 13 & 17 Mtr, Evaporation Area |  |  | 2024-10-04 | Open | 2024-09-27 06:01:54 | 2024-09-27 06:01:54
75 | Unsafe Condition (PIO – UC) | Mechanical | 1 | Dissolver V1-120 A | Kamlesh Patel | Agitator Drive Running Without Belt Guard |  |  | 2024-10-04 | Open | 2024-09-27 06:07:14 | 2024-09-29 16:44:13