## Worksheet
Weakly Report
Start Date |  | End Date
2024-08-21 00:00:00 |  | 2024-08-28 08:55:58
Incident id | Issue Type | Department | Unit No | Location | Reported BY | Issue Description | Serverity Level | Action Details | Target Date | Issue Status | Issue Created | Issue last Updated
34 | Unsafe Condition (PIO – UC) | Civil | 1 | Behind 0-Meter Cabin | Darhit Shah | Cover Plate Found Bend. |  |  | 2024-08-29 | Open | 2024-08-22 09:37:51 | 2024-08-22 09:37:51
35 | Unsafe Condition (PIO – UC) | Civil | 1 | Behind Process Building | Darhit Shah | Pit Cover Found Corroded And Not At Place |  |  | 2024-08-29 | Open | 2024-08-22 09:39:47 | 2024-08-22 09:39:47
36 | Poor Housekeeping | Process / Operation | 1 | PPA & PPA Process Plant several area | Saiyadali | Housekeeping Is Poor, With Spillage Of Sludge Observed In Several Areas. |  |  | 2024-09-03 | Open | 2024-08-27 09:24:20 | 2024-08-27 09:24:20
37 | Unsafe Condition (PIO – UC) | Process / Operation | 1 | PAP Plant Section-2 Evaporation area | Saiyadali | Water Falling Observed On Plant Staircase @ 6 And 13 Meters. |  |  | 2024-09-03 | Open | 2024-08-27 09:28:47 | 2024-08-27 09:28:47
38 | Poor Housekeeping | Civil | 1 | PAP Fire Pump house | Saiyadali | Acidic Water Logging Found Around The Water Reservoir Of The PAP Fire Pump House. |  |  | 2024-09-03 | Open | 2024-08-27 09:33:47 | 2024-08-27 09:33:47
39 | Poor Housekeeping | Process / Operation | 1 | PAP Plant Rockcharging area | Saiyadali | Rock Was Observed On The Fire Water Line, Which Could Damage The Line During Rock Handling By Mechanical Device/Aid. |  |  | 2024-09-03 | Open | 2024-08-27 09:41:40 | 2024-08-27 09:41:40
40 | Unsafe Condition (PIO – UC) | Electrical | 2 | CH-17, below Electrical cable tray | Saiyadali | Oil And Diesel Drums Were Observed Stored Below/near The Electrical Cable Tray, Should Be Removed To Avoid Fire Hazards. |  |  | 2024-09-03 | Open | 2024-08-27 09:46:28 | 2024-08-27 09:46:28
41 | Poor Housekeeping | Process / Operation | 1 | PPA 7100 | Saiyadali | PPA 7100 Road Found Slipparary, It Should Be Cleaned. |  |  | 2024-09-03 | Open | 2024-08-27 09:49:20 | 2024-08-27 09:49:20
42 | Unsafe Condition (PIO – UC) | Electrical | 1 | Power Plant GIS room | Saiyadali | Power GIS Room SF6 Cylinder Lying There, To Be Removed. |  |  | 2024-09-03 | Open | 2024-08-27 09:53:29 | 2024-08-28 05:41:28
43 | Recommendation / CAPA | Safety & Environment | 1 | Entire Plant | Saiyadali | It Was Represented That Quality Of PPEs @ O&M Contractors Is Not Consistent With IS. |  |  | 2024-09-03 | Open | 2024-08-27 09:58:28 | 2024-08-27 09:58:28
44 | Unsafe Condition (PIO – UC) | Process / Operation | 1 | SCP Plant | Saiyadali | There Has Been A Chemical Spillage From The SCP Main Plant 2nd Floor To The Ground Floor Near The Mechanical Cabin, Requiring Attention @ Repair. |  |  | 2024-09-03 | Open | 2024-08-27 10:20:24 | 2024-08-27 10:20:24
45 | Suggestion | Mechanical | 1 | Main Canteen to Power Plant area | Saiyadali | The Natural Gas (NG) Line From The Main Canteen To The Power Plant Canteen Area, Suggested To Be Installed On The Piperack.  Piperack Route Finalization (survey) To Be Done For Further Course Of Action. |  |  | 2024-09-03 | Open | 2024-08-27 10:25:41 | 2024-08-28 05:41:47
46 | Unsafe Condition (PIO – UC) | Process / Operation | 1 | Secondary Brine-3 | Saiyadali | Chlorine Gas Detectors To Be Provided At Secondary Brine – 3 |  |  | 2024-09-03 | Open | 2024-08-27 10:29:39 | 2024-08-27 10:29:39
47 | Poor Housekeeping | Civil | 1 | PAP | Saiyadali | Toilet Block Cleaning Of PAP & PPA Plant Areas To Be Improved. | High |  | 2024-09-03 | Open | 2024-08-27 10:31:42 | 2024-08-27 13:40:56
48 | Unsafe Condition (PIO – UC) | Process / Operation | 1 | PAP Rock Phosphate area | Saiyadali | Rock Phosphate Dusting Hazard To Be Reviewed @ Effective Control Management. | High |  | 2024-09-03 | Open | 2024-08-27 10:33:49 | 2024-08-27 13:25:30
49 | Near Miss | Process / Operation | 1 | At MOV 1132A | P R BHIMANI | There Is No Proper Space For Maintenance. There Is High Chances Of Leg And Head Injury. |  | Utmost Must Be Taken While Maintenance Activity. | 2024-09-04 | Closed Request | 2024-08-28 07:29:47 | 2024-08-28 08:03:43